## Timeline
VoteInformed Intel v2 — Compressed Delivery Timeline
Election Day | 2026-11-03 |  | Legend: yellow cells are editable (dates, Status). Planned dates follow the original INTEL_V2_PLAN.md §5; target dates are the compressed schedule.
As of | 2026-10-02 |  | Source: docs/product/INTEL_V2_PLAN.md (Oct 1, 2026). Status reflects branch 2026Midterm_intel_v2 as of the 'As of' date.
Code freeze | 2026-10-20
Phase | Milestone | Plan ref | Original window | Target start | Target end | Duration (days) | Days before Election Day | Before freeze? | Status | Depends on | Notes
1 · Foundation
1 · Foundation | Hourly Kalshi/Polymarket snapshot cron | §3.2 | Oct 1–7 | 2026-10-02 | 2026-10-03 | 2 | 31 | Yes | Not started | market_snapshots table (done) | Start first: history can't be backfilled.
1 · Foundation | FRED economic indicators ingestion | §3.4 | Oct 1–7 | 2026-10-03 | 2026-10-04 | 2 | 30 | Yes | Not started | indicator_series tables (done) | Yields, curve, S&P 500, VIX, gas, CPI, unemployment.
1 · Foundation | Agent foundation (AgentRun logging, Zod schemas, model routing) | §4.5 | Oct 1–7 | 2026-10-03 | 2026-10-04 | 2 | 30 | Yes | Not started | agent_runs table (done) | Prompt + schema + DB write; no framework.
1 · Foundation | Article / ArticleTag tables + Agent 1 news triage running | §4.2 #1 | Oct 8–14 | 2026-10-03 | 2026-10-04 | 2 | 30 | Yes | Not started | Agent foundation | Pulled forward so Agent 2 has 30 days of articles by Nov 3.
1 · Foundation | District race pages (static data, ACS demographics) | §3.1 | Oct 1–7 | 2026-10-05 | 2026-10-08 | 4 | 26 | Yes | Not started | district_profiles table (done), Census ACS
2 · First agents & index
2 · First agents & index | Win probability index + methodology page | §3.3 | Oct 8–14 | 2026-10-06 | 2026-10-08 | 3 | 26 | Yes | Not started | Snapshots, polls, fundamentals | Computed in code, not by AI.
2 · First agents & index | Agent 3 — Why it moved | §4.2 #3 | Oct 8–14 | 2026-10-07 | 2026-10-09 | 3 | 25 | Yes | Not started | Snapshots, Agent 1, RaceSignalEvent | Event-driven; returns 'no clear cause found' when unsure.
2 · First agents & index | Agent 5 — Daily brief | §4.2 #5 | Oct 8–14 | 2026-10-08 | 2026-10-09 | 2 | 25 | Yes | Not started | Agents 1, 3, 4
3 · Analysis layer
3 · Analysis layer | Biggest movers feed | §3.5 | Oct 15–24 | 2026-10-10 | 2026-10-11 | 2 | 23 | Yes | Not started | Snapshot history, Agent 3
3 · Analysis layer | Agent 2 — District issues | §4.2 #2 | Oct 15–24 | 2026-10-11 | 2026-10-12 | 2 | 22 | Yes | Not started | Agent 1 (30 days of tags)
3 · Analysis layer | Agent 4 — Signal divergence | §4.2 #4 | Oct 15–24 | 2026-10-12 | 2026-10-13 | 2 | 21 | Yes | Not started | Index inputs
3 · Analysis layer | Agent 8 — Ask the race (grounded chat) | §4.2 #8 | Oct 15–24 | 2026-10-13 | 2026-10-15 | 3 | 19 | Yes | Not started | Stored data + articles | Answers only from stored data, with citations.
3 · Analysis layer | Early vote tracker | §3.8 | Oct 15–24 | 2026-10-14 | 2026-10-16 | 3 | 18 | Yes | Not started | State early-vote data | Only states that publish by party.
3 · Analysis layer | Tipping-point races (Monte Carlo) | §3.7 | Oct 15–24 | 2026-10-16 | 2026-10-18 | 3 | 16 | Yes | Not started | Win probability index
4 · Election night
4 · Election night | Decide results feed (AP / DDHQ / state SoS) | §3.6 | Oct 25–Nov 3 | 2026-10-02 | 2026-10-09 | 8 | 25 | Yes | Not started | — | Decide now: contract procurement may outlast the window.
4 · Election night | Freeze + load testing | §3.6 | Oct 25–Nov 3 | 2026-10-19 | 2026-10-24 | 6 | 10 | No | Not started | Phases 1–3 complete
4 · Election night | Agent 7 — Data QA | §4.2 #7 | Oct 25–Nov 3 | 2026-10-19 | 2026-10-22 | 4 | 12 | No | Not started | Ingestion jobs
4 · Election night | Election night live mode | §3.6 | Oct 25–Nov 3 | 2026-10-21 | 2026-10-30 | 10 | 4 | No | Not started | Results feed contract, load test
4 · Election night | Agent 9 — Election night notes | §4.2 #9 | Oct 25–Nov 3 | 2026-10-26 | 2026-10-31 | 6 | 3 | No | Not started | Live mode
5 · After election
5 · After election | Agent 6 — Candidate positions (human review) | §4.2 #6 | After Nov 3 | 2026-11-09 | 2026-11-20 | 12 | -17 | No | Deferred | Admin review queue | Don't pull forward.
5 · After election | Polarization + democratic institutions indexes | §4.4 | After Nov 3 | 2026-11-16 | 2026-12-11 | 26 | -38 | No | Deferred | Published methodology | Don't rush before the election.
5 · After election | Phase 2 — Elections Monitor (2027 gov, 2028 primaries, global calendar) | §6 | After Nov 3 | 2026-12-01 | 2026-12-31 | 31 | -58 | No | Deferred
Summary
Done | 0
In progress | 0
Not started | 19
Blocked | 0
Deferred | 3
Total milestones | 22
% done | 0%

## Data Sources
Data Sources & API Access Needed
Legend: yellow cells are editable (Key obtained?, Owner). 'In codebase' = already wired in backend/src. Cost/terms should be confirmed with each provider before signup.
# | Source | Data provided | Used for | Phase needed | Needed by | Access / endpoint | Auth | Cost (verify) | In codebase? | Key obtained? | Owner | Notes
1 | Kalshi | Election market prices, volume, liquidity | §3.2 snapshots, index, movers, Agent 3/4 | 1 | 2026-10-03 | external-api.kalshi.com/trade-api/v2 | None for public market data | Free | Yes | Yes |  | Already powering live quotes; add hourly storage.
2 | Polymarket (Gamma API) | Election market prices, volume | §3.2 snapshots, index, movers | 1 | 2026-10-03 | gamma-api.polymarket.com | None for public reads | Free | Yes | Yes
3 | FEC OpenFEC | Receipts, cash on hand, committees; Schedule E outside spending | Race pages, index money ratio, Agent 3 triggers, issue #31 | 1 | 2026-10-05 | api.open.fec.gov/v1 | api.data.gov key | Free (rate-limited) | Yes | Yes |  | Schedule E uses the same key.
4 | FRED (St. Louis Fed) | 10Y/2Y yields, yield curve, S&P 500, VIX, gas prices, CPI, unemployment | §3.4 economic indicators | 1 | 2026-10-04 | api.stlouisfed.org/fred | Free API key | Free | No |  |  | FRED carries SP500, VIXCLS, GASREGW, so a separate market-data API may not be needed.
5 | U.S. Census ACS | District demographics (income, education, race, age) | §3.1 race pages, district_profiles | 1 | 2026-10-05 | api.census.gov/data (ACS 5-year) | Free API key | Free | No
6 | 2024 presidential results by district | Presidential margin / partisan lean per district | §3.1 race pages, §3.3 fundamentals | 1 | 2026-10-05 | Dataset download (e.g. The Downballot / Daily Kos Elections) | None (download) | Free; check license | No |  |  | Cook PVI is paid; computing lean from 2024 results avoids that.
7 | unitedstates/congress-legislators + GovTrack | Incumbents, terms, ideology scores | Race pages (incumbent record) | 1 | 2026-10-05 | GitHub raw YAML; govtrack.us/data | None | Free | Yes | Yes
8 | News feeds (RSS / Google News RSS) | Local and national election news | Agent 1 triage → Agents 2, 3, 5, 8 | 1 | 2026-10-04 | Publisher RSS feeds, Google News RSS search | None | Free | No |  |  | Respect publisher terms; store headlines/links/snippets.
9 | News API (optional: NewsAPI, GNews, etc.) | Searchable article metadata | Agent 1 coverage beyond RSS | 1 | 2026-10-04 | Vendor REST API | API key | Free tier limited; paid for production | No |  |  | Pick one vendor; free tiers often bar commercial use.
10 | LLM provider (Gemini — existing) | Tagging, explanations, briefs, grounded chat | All agents | 1 | 2026-10-04 | Google Gemini API | API key | Pay per token | Yes | Yes |  | Plan: cheap model for triage, stronger for Agents 3/5/8.
11 | Public polling data | Polls for polling average | §3.1, §3.3 index | 2 | 2026-10-06 | Source TBD (aggregator CSV or curated entry) | Varies | TBD | No |  |  | No free official API; decide source. Pages show 'No public polling' when none exist.
12 | Early vote data | Ballots returned by party registration | §3.8 early vote tracker | 3 | 2026-10-14 | State election office files; U.S. Elections Project | Mostly none | Free | No |  |  | Only states that publish party breakdowns.
13 | Election results feed (AP Elections API or Decision Desk HQ) | Live results, race calls | §3.6 live mode, Agent 9 | 4 | 2026-10-09 | AP Elections API / DDHQ API | Commercial contract | Paid — contract required | No |  |  | Decide by Oct 9; procurement is the main risk. Fallback: state SoS results pages.
14 | State SoS results pages (fallback) | Official live/unofficial results | §3.6 fallback | 4 | 2026-10-21 | Per-state results sites / feeds | None | Free | Partial (placeholder) |  |  | Formats differ per state; scrape only where permitted.
15 | Voteview (DW-NOMINATE) | Party gap in ideology | §4.4 polarization index | 5 | 2026-11-16 | voteview.com data downloads | None | Free | No |  |  | Post-election.
16 | Pew / ANES | Affective polarization survey data | §4.4 polarization index | 5 | 2026-11-16 | Dataset downloads (registration for ANES) | Account | Free | No |  |  | Post-election.
17 | V-Dem, Freedom House, Bright Line Watch | Democratic-institutions measures | §4.4 institutions tracker | 5 | 2026-11-16 | Dataset downloads | None / registration | Free | No |  |  | Post-election.
New API keys / contracts still to obtain |  |  |  | 11
Needed for Phase 1 |  |  |  | 5